## Slide 1: Stormberg Foods: October progress
EXECUTIVE STATUS
Follow-up on the commitments in the October 1–9 update
Brooklyn Biltong · Ayoba Foods · Beg & Barker
October 14, 2026

## Slide 2: The actions are live and purchases are picking up
2 → 15
Meta-attributed purchases
Oct 1–5 vs. Oct 6–13
2.3x
Daily Meta investment
$72 → $166 per day
$2,074
Email and SMS sales
Brooklyn, Oct 1–14 (31 orders)
What you need to know
Execution: every Meta commitment is live across all 3 brands, and we restructured retargeting on October 10.
Results: purchases are up sharply, but Meta return (0.76x) is still below breakeven. Budget has already moved toward what converts best.
What's next: Brooklyn's Fast Sale (Oct 15–18) is the biggest lever of the month.

## Slide 3: October 9 commitments: status by brand
Brand | Commitment | Status | Where it stands
Brooklyn | New-customer campaign on Meta | Done | Live since Oct 5. On Oct 13 we trimmed its budget ($1,000 → $800) due to a high cost per purchase
Brooklyn | Offer vs. No-Offer A/B test | Done | Closed Oct 6; 10%-off new-customer ad sets launched Oct 7
Brooklyn | Smile / W10 program | Done | List-based and lookalike audiences live on Meta; $210 invested
Brooklyn | Game Day email and SMS (Oct 11) | Done | Sent to 6,770 emails and 308 SMS: 7 orders, $585
Brooklyn | Fast Sale VIP 20% / list 15% | On track | 6 sends built: launch Oct 15, reminder Oct 16, last call Oct 18
Brooklyn | Recurring → Subscription flow | In setup | Built and in testing; not live yet
Ayoba | New customers + Smile10 on Meta | Done | 3 purchases at $26 each: the lowest cost per purchase in the portfolio
Beg & Barker | New customers + new BARK15 Welcome | Done | Campaign live since Oct 7 (budget $200 → $300); Welcome live since Oct 6
All 3 brands | Dynamic retargeting (added) | Done | Oct 10: catalog ads to 90-day viewers and cart adders, excluding buyers

## Slide 4: Meta: more volume, efficiency still being built
Chart: Meta-attributed purchases by brand
| Brooklyn | Ayoba | Beg & Barker
Oct 1–5 (5 days) | 0 | 1 | 1
Oct 6–13 (8 days) | 9 | 4 | 2
What's working
Ayoba new customers: $26 per purchase, 1.6x return
Brooklyn dynamic retargeting: $26 per purchase, 2.9x return
Beg & Barker dynamic retargeting: 3.1x return
What we're fixing
Brooklyn new customers: $170 per purchase → budget trimmed on Oct 13
New retargeting (since Oct 10) is still learning; budget raised for Ayoba and Beg & Barker
Source: Meta Ads Manager, platform-attributed purchases and return. Excludes Google Ads and total store sales (see dashboards).

## Slide 5: Brooklyn: email and SMS are driving repeat sales
$2,074
in email and SMS-attributed sales,
Oct 1–14
31
orders; 17 came in automatically through flows
Chart: Sales by program (USD)
| Other flows and sends | $10-off reminder | Win-back | SMS Welcome | Game Day (email + SMS) | First-purchase flow
Sales by program (USD) | 266 | 145 | 166 | 265 | 585 | 647
Game Day had a 60% open rate. The Subscribe & Save and Second Order flows have been live since Oct 7.
Source: Klaviyo (Brooklyn Biltong), platform-attributed orders.

## Slide 6: Next two weeks
Oct 15
Brooklyn Fast Sale
VIP (2+ orders) 20%, rest of list 15%
Oct 16–18
Reminder and last call
Email to VIP and full list
Week of Oct 20
Scale the winners
More budget to retargeting and Ayoba new customers; less to what's expensive
October
Retention
Recurring → Subscription (Brooklyn), SMS Welcome (Beg & Barker), Ayoba flows
Proposed for Wednesday's meeting
Target cost per new-customer purchase by brand
Fast Sale results vs. September's promotional week